ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Beneficiary country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	4

2.2.	Purpose	4

2.3.	Results to be achieved by the Contractor	5

3.	ASSUMPTIONS & RISKS	6

3.1.	Assumptions underlying the project	6

3.2.	Risks	6

4.	SCOPE OF THE WORK	6

4.1.	General	6

4.2.	Specific work	6

4.3.	Project management	8

5.	LOGISTICS AND TIMING	8

5.1.	Location	8

5.2.	Start date & Period of implementation of tasks	8

6.	REQUIREMENTS	10

6.1.	Staff	10

6.2.	Office accommodation	11

6.3.	Facilities to be provided by the Contractor	11

6.4.	Equipment	11

7.	REPORTS	11

7.1.	Reporting requirements	12

7.2.	Submission and approval of reports	12

8.	MONITORING AND EVALUATION	12

8.1.	Definition of indicators	12

8.2.	Special requirements	12

# BACKGROUND INFORMATION

## Beneficiary country

Republic of Macedonia

## Contracting Authority

Association for Democratic Initiatives (ADI) Gostivar

## Country background

The project “Civil society in action for equality!” is implemented in the frame of IPA National Programme for Transition Assistance and Institutional building 2011. Grant scheme “Further development and Financial Sustainability of the Civil Society” EuropeAid/136-625/ID/ACT/MK. The project is funded by the European Union, implemented by Central Financing and Contracting department, within the Ministry of Finance and the General Secretariat of the Government. The coordinator is Association for Democratic Initiatives (ADI) Gostivar and co-beneficiaries are: Association InSoC – Initiative for social change, Community Center "Drom” – Kumanovo. Over the past several years our country has developed an antidiscrimination legal framework that can be considered as a relatively solid foundation based on which case law will be generated in the future. The national legislation began with explicit prohibition of discrimination through the enactment of several laws, among which especially important were those in the area of labor, which culminated in 2010 with the enactment of the Law on Prevention and Protection from Discrimination (LPPD). This Law is expected to fill the legal gaps that exist in our legal system in the area of non-discrimination and to provide legal protection for all the persons that would appear as alleged victims of discrimination.

The process of adopting Antidiscrimination Law was quite controversial and its full harmonization with the EU legislation is still an arguable issue. The Law does not explicitly prohibit discriminatory job advertisements or statements on the grounds of age or mental and physical disability while the strongest prejudice and knowledge gap exist in the area of discrimination based on sexual orientation. In accordance with positive legislation, the institutions in charge adopted a number of national strategies to combat discrimination such: as National Strategy on Equality and Non-discrimination on the ground of Ethnicity, Age, Mental and Physical Disability and Sex 2012-2015; National Strategy for Gender Equality 2013-2020; National Strategy for Poverty Reduction and Social Exclusion in the Republic of Macedonia for 2010-2020 as well with the Roma Inclusion Decade and its action plans etc. Despite the legal provisions, surveys regularly show that the discrepancy between the levels of discrimination experienced and discrimination reported needs to be seriously addressed. Victims still have difficulty in recognizing a discriminatory situation. Awareness is low not only among the public but also among the members of the public intuitions.

## Current situation in the sector

Given that equality legislation, by itself, is unlikely to be sufficient to achieve desired changes in equality outcomes for individuals; non-discrimination/equality mainstreaming has an important role to play in complementing and reinforcing anti-discrimination legislation across the grounds of discrimination covered. The aim of non-discrimination mainstreaming is ultimately to reduce levels of discrimination suffered by particular vulnerable social groups (as well as those at risk of multiple discrimination) and to improve equality outcomes for individuals.

To be effective non-discrimination/equality mainstreaming requires a support infrastructure to fully realise its potential benefits. This includes leadership, coordination structures, guidance materials, trainings, expert support, participation, legislative requirements, and data. In this regard it is important to improve the way inequality and discrimination is tackled locally and how the national strategies are reflected in the local policies and practices. The effective equality infrastructure support need to be built starting from the local level and involving all relevant stakeholders: civil society organizations (CSOs) representing the interests of those at risk of experiencing inequality; local institutions which are expected to guarantee and promote equal treatment and non-discrimination; Local commissions for interethnic relations and for equal opportunities have mandate to ensure active participation of minority groups/women in the decision-making process and to ensure institutional dialogue between different ethnic groups; Commission for Protection from discrimination as national equality body and the Ombudsman - National Human Rights Institution  are obliged by law and pledge to cooperate with large range of stakeholder to reach their common goals – equality of opportunities to all. They all are target group of the project action.

## Related programmes and other donor activities

The project action is related with most of the ADI activities in the area of promotion of human and minority rights, supporting democracy through monitoring of the political reforms and processes. ADI has provided numerous trainings on respective international / national instruments and institutions that deal with the issues of human rights and human rights protection. ADI is one of the founders of the National Alliance Macedonia without Discrimination in 2009 with the aim to contribute towards creating a fair society without discrimination. Previously this body has contributed in the process of drafting the Antidiscrimination Law and Anti-Discrimination Strategy in the country.

DROM is a Roma NGO founded in Kumanovo in 1997. DROM works with the most vulnerable groups in the society in order to improve access to social services through education about social rights and anti-discrimination legislation; improve labour market potential of young people and women from Roma ethnic community in the labour market by mediating, provision of skills or preparation for self- employment; field work and collecting information’s about the actual problems among the Roma population.

InSoc was created in 2009 on initiative of Roma NGOs to support the implementation of activities of Roma NGOs. Since its establishment InSoc works to increase capacities of Roma for sustainable social inclusion and participation in development processes in Macedonia, with particular focus on integration, anti-discrimination and desegregation; Including Roma in all phases of the projects is at the heart of the proposed intervention.

The proposed activity is building on the results and experience of the previous projects of partner organisations, which were focused on strengthening cooperation between local authorities and civil society, multi-stakeholder community development processes and social inclusion of the vulnerable groups. The project action will streamline the anti-discrimination and equality policy, thus contributing to the effective implementation of the national human rights standards and minority protection in the country and the further alignment with the EU Non-discrimination and Equality standards especially the EU Charter and the two Anti-discrimination directives (2000/78 and 2000/43). The action will position itself among other existing initiatives, aimed at building capacity and cooperation between different stakeholders in the field of non-discrimination and seek good practice of implementation.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

- To support the active involvement of civil society in implementing antidiscrimination policies and practices at local level.

- To enhance capacity of the civil society organizations to promote and monitor the anti-discrimination standards and equality;

- To strengthen the inter-institutional cooperation for prevention and fight against discrimination at local level;

- To raise awareness on anti-discrimination legislation and to promote the concept of equality.

## Purpose

The purposes of this contract are as follows:

- Purpose 1: Conducting stakeholders/needs analysis on current situation with regard to non-discrimination and equality. This initial need assessment will help to identify:

- Needs and gaps on the cooperation between the local CSOs, local institutions, and local commissions as well their relations with the national Commission for Protection from Discrimination and the Office of the Ombudsman;

- Capacity needs assessment of different stakeholders, their mutual interests and potential barriers for collaboration;

- Availability of public services to various vulnerable social groups;

- The need analysis is envisioned to be comprised of focus groups interviews to be conducted with the participants of the local CSOs, relevant representatives of the Centres for Social Work, Agencies for employment, local commissions, Courts, social partners (employer organisations, trade unions) and local media. The findings from the focus groups will be used for initial mapping of the local capacities, their experience to work on anti-discrimination, perception of their mutual interests and identification of priority for intervention.

- The data collected in course of interviews will be used for development of set of questionnaires, which will be widely disseminated among representatives of all stakeholder groups involved in the project. They will provide an insight into positions and needs of the organizations/groups, which will later be involved in the project activities as well into initial level of cooperation at the start of the project. The content of questionnaires will thus be developed according the priorities identified within the focus groups and in a manner which will allow monitoring of the process of attaining the project's aims and results. The questionnaires will be focused on: operating environment of the organisation/institution, knowledge and experiences on non-discrimination policies and equality challenges as well inter institutional collaboration. In each of the included municipalities Gostivar, Tetovo, Kumanovo, Prilep, Bitola, Berovo, Shtip and Shuto Orizari the interviews should be conducted with 15-20 stakeholders.

- This analysis will serve as background document providing input to the capacity building specifications and will help to identify the target groups in particular local CSOs active in the anti-discrimination and other relevant local stakeholders for participation in the trainings and their needs; moreover it will give valuable inputs for all future activities in the project and will also set baseline values for certain indicators, that will be re-checked at the end of the project.

- Purpose 2: Targeted capacity-building activities

- These activities will include delivering comprehensive training program focused on non discrimination and equality for the local civil society organizations, local institutions, Commission for interethnic relations and Commission for equal opportunities, social partners and media from the target municipalities. In total three trainings (2 day each) will be conducted gathering at least 20 participants per training/60 in total. The focus and level of training will be considered carefully and matched to the participants needs in order the training to have the desired result. Therefore, the content of the training will be developed according to the findings from the need assessment but at least the following topics will be covered:

- A European Union framework for non-discrimination/equality mainstreaming;

- National non-discrimination legislation;

- The procedures for implementation of the right of equal treatment and;

- The Mandate of the protective mechanisms i.e. national Commission for protection from Discrimination and the Ombudsman Institution;

- All these topics should be provided in the training material and presented during the trainings.

- Purpose 3: Training on advocacy and lobbying for the local civil society organizations

This activity will include training on advocacy and lobbying methods and techniques for 20 CSOs representatives from the target municipalities. The training will be delivered in two (2) days. The focus of the training should be identifying the gaps in advocacy activities and developing towards “opportunities” in advocacy. The capacities of the local CSOs to carry out future advocacy strategies can only be strengthened by using the know-how of the networks members according to their expertise and contacts. For the capacity building of CSOs to develop advocacy strategies it is of utmost importance that the methodology how to efficiently and effectively develop such strategies follows recognized principles, no matter what subject the advocacy strategy is about. These principles are: (1) goal of the advocacy strategy; (2) audiences, key-players, stakeholder; (3) messages; (4) messengers; (5) delivery; (6) resources; (7) gaps; and (8) evaluation. All these principles should be incorporated in the training material and presented during the training.

## Results to be achieved by the Contractor

- Result 1: Prepared methodology for assessment;

- Result 2: Conducted eight (8) focus groups meetings;

- Result 3: Develop set of questionnaires and collecting data;

- Result 4: Produced background document;

- Result 5: Developed training material non-discrimination/equality;

- Result 6: Conducted three (3) trainings on non-discrimination/equality – two (2) days each training/ six (6) days in total;

- Result 7: Developed training material on advocacy and lobbying

- Result 8: Conducted one (1) training on advocacy and lobbying – two (days) in total.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

CSOs, institutions and other stakeholders will participate in the activities (send participants to trainings, workshops, meetings provide data for the research, work on development of procedures for dealing with victims of alleged discrimination);

CSOs will use the knowledge gained on trainings, results from the research and procedures, to advocate for reforms and policy changes;

## Risks

Sufficient number of stakeholders showing their interest for participation/involvement.

# SCOPE OF THE WORK

## General

### Description of the assignment

The contract will provide expert support during the implementation of the project activities related to need assessment, capacity building and advocacy and lobbying in the area of non-discrimination, equality and human rights as listed under point 2.2.

The offers can be submitted, both, by individuals and legal entities. In case if the Contractor/Consultant is a legal entity, it must offer experts and trainers experienced in providing/implementation of similar activities. The proposed experts must satisfy the criteria described under section 6.

### Geographical area to be covered

The activities will be realized in the municipalities of  Berovo, Kumanovo, Stip, Suto Orizari, Tetovo, Gostivar, Prilep and Bitola.

### Target groups

Local CSOs, relevant representatives of the Centres for Social Work, Agencies for employment, local commissions, Courts, social partners (employer organisations, trade unions) and local media.

## Specific work

The contractor should undertake the following activities in order to achieve the contract results/job description:

Activity 1: Conducting stakeholders/needs analysis. The need assessment of current situation with regard to non-discrimination and equality at local level will be realized through the methods of focus groups interviews and dissemination and collecting of questioners to the project target groups in each municipality. The contractor should conduct focus groups interviews with local CSOs, relevant representatives of the Centres for Social Work, Agencies for employment, local commissions, Courts, social partners (employer organisations, trade unions) and local media. One (1) focus group per each municipality will be conducted - eight (8) focus groups in total.

Based on focus groups findings the contractor will develop set of questionnaires to be disseminated among representatives of all stakeholder groups involved in the project - local CSOs, relevant representatives of the Centres for Social Work, Agencies for employment, local commissions, Courts, social partners (employer organisations, trade unions) and local media. It is expected 15-20 questionnaires to be collected per municipality.

The data collected through focus groups interviews and answers from the questionnaires will be used  a background document to be provided. This document should provide input to the capacity building specifications and will help to identify the target groups in particular local CSOs active in the anti-discrimination and other relevant local stakeholders for participation in the trainings and their needs; moreover it will give valuable inputs for all future activities in the project and will also set baseline values for certain indicators, that will be re-checked at the end of the project.

The contractor will be responsible to develop methodology for need assessment, conduct eight (8) focus groups, prepare and distribute the questionnaires, collect data, prepare the final report/background document. A total of 40 working days has been allocated to complete this activity. The period of implementation is February – March 2016.

Activity 2: Targeted capacity-building activities

In total three trainings (2 day each) will be conducted gathering at least 20 participants per training/60 in total. The participants will be local civil society organizations, local institutions, Commission for interethnic relations and Commission for equal opportunities, social partners and media from the project target municipalities. The focus and level of training will be considered carefully and matched to the participants needs in order the training to have the desired result. Therefore, the content of the training will be developed according to the findings from the need assessment but at least the following topics will be covered:

- A European Union framework for non-discrimination/equality mainstreaming;

- National non-discrimination legislation;

- The procedures for implementation of the right of equal treatment and;

- The Mandate of the protective mechanisms i.e. national Commission for protection from Discrimination and the Ombudsman Institution;

Trainings will provide an opportunity to explain the content of EU antidiscrimination directives and their transposition in the national legislation to potential victims, as well as alleged discriminators in order to combat unequal treatment and promote equality. Besides the theoretical component of the training the emphases will be put on the wide variety of concrete problems related to discrimination in the local communities and propose/finding solutions to them.

The contractor will be responsible to develop training program, implement the trainings and prepare final report from the trainings. A total of 32 working days has been allocated to complete this activity. The period of implementation is March - April 2016.

Activity 3: Training on advocacy and lobbying for the local civil society organizations

This activity will include training on advocacy and lobbying methods and techniques for 20 CSOs representatives from the target municipalities. The training will be delivered in two (2) days. The focus of the training should be identifying the gaps in advocacy activities and developing towards “opportunities” in advocacy. The capacities of the local CSOs to carry out future advocacy strategies can only be strengthened by using the know-how of the networks members according to their expertise and contacts. For the capacity building of CSOs to develop advocacy strategies it is of utmost importance that the methodology how to efficiently and effectively develop such strategies follows recognized principles, no matter what subject the advocacy strategy is about. These principles are: (1) goal of the advocacy strategy; (2) audiences, key-players, stakeholder; (3) messages; (4) messengers; (5) delivery; (6) resources; (7) gaps; and (8) evaluation. All these principles should be incorporated in the training material and presented during the training. A total of 10, 6 working days has been allocated to complete this activity. The period of implementation is October - November 2016.

The contractor will be responsible to develop training program, implement the trainings and prepare final report from the trainings.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See http://ec.europa.eu/europeaid/funding/communication-and-visibility-manual-eu-external-actions_en .

## Project management

### Responsible body

The Contracting Authority- Association for Democratic Initiatives (ADI)  Gostivar is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be also performed by Association for Democratic Initiatives (ADI) as coordinator and co-beneficiaries are: Association InSoC – Initiative for social change – Skopje and Community Center "Drom” – Kumanovo. ”. The project is implemented in the frame of IPA National Programme for Transition Assistance and Institutional building 2011. Grant scheme “Further development and Financial Sustainability of the Civil Society” EuropeAid/136-625/ID/ACT/MK. The project is funded by the European Union, implemented by Central Financing and Contracting department, within the Ministry of Finance and the General Secretariat of the Government.

### Management structure

The overall responsible for the implementation of the whole action is the Executive Director as a legal representative of the Contracting Authority. In this sense, all financial arrangements must be confirmed by the Executive Director.

The project management will be performed jointly by the following team: ADI Project Manager will be responsible for overall coordination of the action and communication among partners, with stakeholders, media and general public. ADI Project officer responsible for providing administrative and technical support to the project manager and other members of the project team. This also includes establishment of communication, documentation, and reporting structures and procedures; dissemination of relevant information, collection of data, reports, etc. DROM and InSoc project assistants are responsible for providing input and an ongoing assistance in all aspects of the program that require specific expertise

### Facilities to be provided by the Contracting Authority and/or other parties

The Contracting Authority will provide all necessary facilities, including printing of the questionnaires, agendas for the events, training materials.

# LOGISTICS AND TIMING

## Location

The operational base for the project is ADI office in Gostivar. The activities carried out by the Consultant will be in the municipalities of Berovo, Kumanovo, Stip, Suto Orizari, Tetovo, Gostivar, Prilep and Bitola.

## Start date & Period of implementation of tasks

The intended start date is 3 February 2016 and the period of implementation of the contract will be ten (10) months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed Statements of Exclusivity and Availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

Key expert 1: Team Leader

Qualifications and skills

- University degree;

- Master degree will be an asset;

- Strong analytical skills and report writing abilities;

- Good interpersonal skills, clear communication and ability to establish working relationships with institutional stakeholders and civil society;

General professional experience

- Minimum five (5) years of professional experience in research and analysis in the fields of non-discrimination, equality, human rights,  capacity building activities and trainings.

Specific professional experience

- Assignments/experiences in developing /implementing of research and analysis in the field of non-discrimination, equality,  human rights, capacity building activities and trainings.

Key expert 2:

Qualifications and skills

- University degree ;

- Master degree will be an asset;

- Excellent communication and organization skills;

- Creative and constructive person;

General professional experience

- Minimum five (5) years of professional experience in civil society development and strengthening of the capacities of civil society organizations (CSOs)/institutions.

Specific professional experience

- Assignments/experiences in developing and implementing civil society projects and capacity building activities related to equality, human rights as well advocacy and lobbying for the involvement of the CSOs in policy making process.

Key expert 3:

Qualifications and skills

- University degree or relevant specific experience ;

- Communication and organization skills;

- Analytical skills and report writing abilities;

General professional experience

- Minimum three (3) years of professional experience in developing /implementing projects, research and analysis in the field of non-discrimination, equality, human rights.

Specific professional experience

- Assignments/experiences in developing /implementing projects, research and analysis in the field of non-discrimination, equality, human rights.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.<

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English in one original and tree (3) copies, (double sided printing):

- Interim Report of maximum 12 pages to be produced after 3 months, from the start of implementation

- Draft final report of maximum 20 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 60 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on the tender. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

- Prepared methodology for assessment for local needs related to non-discrimination and equality;

- Conducted eight (8) focus groups meetings;

- Develop set of questionnaires and collecting data of at least 15-20 stakeholders from each municipality;

- Produced background document;

- Developed training material non-discrimination/equality;

- Conducted three (3) trainings on non-discrimination/equality – two (2) days each training/ six (6) days in total;

- Developed training material on advocacy and lobbying;

- Conducted one (1) training on advocacy and lobbying – two (days) in total.

## Special requirements

N/A